## Summary
AiRev pending reviews — summary for management
As of 3 Sep 2026 · Upskillize EcoPro LMS · 30 Days 30 AI Tools cohort
Rows showing as "pending review" | 1157 | Admin header showed 1,146–1,152 during the day; the DB snapshot is the number used here.
…that only the STUDENT can fix | 788 | Private links, dead links, empty submissions, wrong work. Re-running these costs money and changes nothing.
…that WE must fix (re-run) | 344 | 261 grade-guard refusals + 29 rubric-cache failures + 54 never reviewed. One re-run with a healthy provider.
Share that is the student's to fix | 68.11%
Estimated cost to re-run our 261 | 9.6087 | Blended estimate. Editable assumptions on the Cost sheet — measure 5 rows first, then update.
Same, in INR | 807.1321
Spent so far on the failed loop (reported) | 120 | The sweep re-bought the same unreadable rows every 3 hours with no spending cap. Now capped.
What went wrong, in one line each
1. Most "pending" rows were not waiting for a marker. AiRev had already looked, found nothing it could read, and refused — but nobody told the student.
2. A link pasted in the submit form's link field went to the file downloader, never the browser. 335 link submissions were refused without ever being opened as a page.
3. When the AI provider went down, the sweep kept re-buying the same failed rows every 3 hours. The safety brake never fired because a provider failure was counted as a policy skip.
4. Every review runs on the staff key, so none of it appeared in the credit ledger. The bill was the first visible number.
What is done / what is next → see Action plan sheet

## Breakdown
Pending review — what each row actually is
30 Days 30 AI Tools (course 55). DB snapshot 3 Sep 2026, 12:55 IST. Live counts drift by a few as students submit.
# | Reason (what AiRev found) | Rows | Whose move | What the student must do | What we must do | Status | Re-run cost?
1 | Link answered 401/403 or asked for a sign-in | 72 | Student (mostly) | Open the link in a private window. If it asks to sign in, change sharing to "Anyone with the link can view". Submit again. | Some are public pages that block bots (Canva, Notion). Fixed: a link in the link field now opens in the browser renderer, not the raw downloader. | Fix built, awaiting deploy | No — send back
2 | Link dead — 404, host not found, redirect loop | 20 | Student | Check the address, or upload the file instead. Submit again. | — | Ready to send back | No
3 | Link opened, nothing readable on it (video/design page) | 263 | Student (partly) | Add 3–4 lines on what you made and how. Submit again with the link. | Same renderer fix as #1 applies — some of these will now read. | Fix built, awaiting deploy | No — send back
4 | Different work from what the brief asked | 69 | Student | Read the brief again. Submit the work it asks for. | Admin reads the 69 evidence lines before sending (panel shows what AiRev saw). | Ready to send back | No
5 | File opened but had no readable text (blurry scan/photo) | 4 | Student | Sharper scan, or type the answer as well. Submit again. | — | Ready to send back | No
6 | Nothing readable arrived — no file and no written answer | 360 | Student | Attach the file again or type the answer. Check it opens on your device first. Submit again. | Add a submit-time check so an empty submission is refused at once, not days later. | Submit-time check not built | No
7 | Grade guard refused: under 50% of the brief's requirements got a verdict | 261 | Us | Nothing — their work is fine. | Re-run once now the AI provider is healthy. Rows still refused after that point to a requirement the deliverable cannot show → tighten the derivation rule. | Waiting for one re-run | YES — see Cost sheet
8 | Task requirements could not be read from cache | 29 | Us | Nothing. | Same re-run. | Waiting for one re-run | YES — see Cost sheet
9 | Never reviewed at all (queued, never picked up) | 54 | Us | Nothing. | Next sweep picks them up once the sweep is switched back on. | Waiting for sweep | Yes — first review
10 | Refusal wording not recognised | 1 | Check by hand | — | Look at the row. | Open | —
11 | Other courses (not 30 Days) | 24 | — | — | Out of scope for this exercise. | — | —
| TOTAL pending (all reasons) | 1157
| Student's move (rows 1–6) | 788
| Our move (rows 7–9) | 344
| Share that is the student's to fix | 68.11%
Source: assignment_submissions joined to assignments, course_id = 55, grade IS NULL, feedback carrying AiRev's notGraded verdict; reasons read from the stored message text. Counts supplied from the LMS database on 3 Sep 2026.

## Re-review cost
Estimated cost to re-run the rows we failed
Blue = editable assumption. Yellow = update after measuring 5 rows on /health. Everything else is a formula.
Input / result | Value | Note
Rows to re-run (grade guard refusals) | 261 | From the DB reason count (178 + 83). Add the 29 rubric failures if running those too.
Spent so far on the failed loop (USD) | 120 | As reported by Upskillize on 3 Sep. Not measured by this sheet.
Model prices (verify on the Anthropic console)
Claude Haiku 4.5 — input, USD per 1M tokens | 1 | Assumed list price. Update from console.
Claude Haiku 4.5 — output, USD per 1M tokens | 5 | Assumed list price. Update from console.
Whisper transcription, USD per minute | 0.006 | Assumed list price. Only video/audio rows pay this.
Per-row token assumptions (measure, then overwrite the yellow cells)
Input tokens per review call (brief + requirements + submission) | 12000 | Typical for a text/PDF row. Measure: /health spend before/after 5 rows ÷ 5.
Output tokens per review call | 2500 | Structured review JSON + feedback.
Share of rows needing the strong-tier retry | 30% | Same model with extended thinking; fires when the first pass is thin.
Token multiplier on a retry | 1.5 | Thinking budget adds output tokens.
Share of the 261 that are video/audio | 40% | Day 17 is a video day; the mix is a guess until measured.
Average recording length (minutes) | 2
Frames sampled per video | 6
Input tokens per sampled frame (vision) | 1600
USD → INR | 84 | Update to today's rate.
Results
Review call cost per row (text/PDF) | 0.028175 | (input×price + output×price) with the retry share blended in.
Extra cost per VIDEO row (transcription + frames) | 0.0216 | Whisper minutes + one vision read per frame.
Cost per text row | 0.028175
Cost per video row | 0.049775
Blended cost per row | 0.036815 | Weighted by the video share above.
TOTAL to re-run the rows above (USD) | 9.6087
TOTAL in INR | 807.1321
…as a share of what the failed loop cost | 8.007% | The re-run is a small fraction of what was burned re-refusing unreadable rows.
Cost if a row were run TWICE by mistake (the old behaviour) | 19.2174 | The attempt ceiling now stops every row at 2 tries; the brake stops a dead-provider run after 8 rows.
How to replace the estimate with a measurement (10 minutes)
1. Read GET /health → spend.unbilled_input_tokens and unbilled_output_tokens (note both).
2. POST /api/review/jobs/sweep?limit=5 with the admin key. Wait ~5 minutes.
3. Read /health again. (after − before) ÷ 5 = real tokens per row. Type them into C14 and C15.
4. The totals above recalculate. Then run the rest.

## Action plan
Action plan — in the order it must happen
Each step depends on the one above it.
# | Action | Why in this order | Owner | Cost | Status
1 | Deploy the four AiRev fixes (attempt ceiling, brake, spend counter, link-field renderer) | Nothing below is safe to run until the sweep cannot loop and a link can be opened as a page. | Ranjana | — | Committed; push pending
2 | Deploy the LMS changes (Waiting-on-students panel, returned-row resubmit, student card) | The send-back must be readable and resubmittable before anyone is sent back. | Ranjana | — | Panel live; rest on disk
3 | Read the 69 "different work" evidence lines in the panel; untick any the admin disagrees with | Only bucket where a human's judgement matters before sending. | Admin | — | 5 minutes
4 | Probe 20 of the link rows on the new code (sweep?limit=20) | Tells us how many "could not open" links were public all along. Avoids telling those students to fix nothing. | Ranjana | ~20 rows | Not started
5 | Send the student-side rows back with the reason-specific note | Removes them from the queue; they can no longer be re-bought by any sweep. Grade stays empty — no zeros. | Admin | ₹0 | Button ready
6 | Measure 5 rows on /health, update the yellow cells on the Cost sheet | Replaces the estimate with a real number before spending on 261. | Ranjana | 5 rows | Not started
7 | Switch the sweep back on (remove SWEEP_MAX_PER_RUN=0) | With the student rows gone, the only eligible rows are ours: 261 + 29 + 54. Two ticks clears them. | Ranjana | See Cost sheet | Not started
8 | Rows still refused after step 7 → tighten the requirement-derivation rule | If the guard refuses again with a healthy provider, the brief asks for something the deliverable cannot show. One prompt change, then re-derive. | Ranjana | Small | Depends on 7
9 | Build the submit-time check: empty submission or bare link refused at once | Stops the pile refilling. Today a student learns days later; they should learn in the same minute. | Ranjana | — | Not built
10 | Build an intake cache so any future re-review skips OCR/transcription | Every re-review today re-reads the file at full price. Not needed for this run; needed before the next rules change. | Ranjana | — | Not built